FAITHSTREAM MARKETING ACTIVITY PLAN [NOVEMBER 2025 - FEB 2026]

EXECUTIVE SUMMARY

FaithStream is launching as Africa's premier faith-based streaming platform, targeting 700M+ Christians across Sub-Saharan Africa and the diaspora. This three-phase GTM plan leverages House of Faith's ecosystem to build anticipation, drive adoption, and establish market dominance in the faith-based entertainment sector.

Following the successful announcement of FaithStream and the availability of thefaithstream.com on 26 Nov 2025, plans have now begun for the global launch event to be held in Lagos, Nigeria. The first FaithStream original will also premiere around this launch event.

This plan highlights the 4 key jobs to be done: Lagos Launch Event, Movie Premiere, Product Marketing, and Social Editorial Management.

Key Success Metrics

| Metric | Target | Timeline |
| --- | --- | --- |
| Waitlist Sign-ups | 10,000 | Nov 30 - Jan 15 |
| Active Subscribers | 50,000+ | Feb 2026 |
| Media Impressions | 10M+ | Mar 2026 |
| Media Coverage | 50+ outlets | Mar 2026 |
| Geographic Reach (comms) | 15 countries | Jun 2026 |

CORE OBJECTIVES

- User Growth: 10K waitlist by Dec 31 → 50K+ app users by Feb 2026

- Fundraising: Drive donations via HOF corporate + FaithStream channels (individual + corporate donors)

# (I) LAGOS LAUNCH EVENT - January 16, 2026

| # Phase | # Key Activities |
| --- | --- |
| # Concept | # “The Gift Unwrapped” - revealing FaithStream to Africa. # Venue: Eko Hotel (150-200 guests). # Red carpet premiere of 'Love & Porridge'. Live product demo. |
| # Pre-Event (Dec 15 - Jan 15) | # Media invites to Nollywood/entertainment press, tech journalists (Dec 20) # Guest invites: performer, producers, pastors, donors, influencers, early supporters (Dec 22) # Countdown social campaign continuation + venue teasers (Jan 1-15) # Press kit distribution with embargoed assets (Jan 10) - Co-founders’ media rounds |
| # Event Day (Jan 16) | # Red carpet arrivals + media wall interviews # Co-founders keynote + FaithStream live demo # 'Love & Porridge' premiere screening # Real-time social posting + live stream highlights # Donor recognition + partnership announcements |
| # Post-Event (Jan 17-31) | # Press release distribution + media follow-ups # Event highlights reel across all social channels # Thank you emails to attendees with app download CTA # Interview clips for ongoing PR push - Co-founders’ media rounds |

# (II) 'LOVE & PORRIDGE' - FaithStream’s First Original

- Teaser trailer release (Jan 2-8) - 30-sec clips across social + YouTube

- Cast & creator spotlights (Jan 6-14) - behind-the-scenes content, interviews

- Full trailer release (Jan 10) - premiere announcement push

- Media screenings (Jan 13-15) - select critics + influencer previews for reviews

- Lagos premiere (Jan 16) - red carpet event, cast Q&A

- Global availability (Jan 16) - exclusive on FaithStream app

- Post-launch buzz (Jan 17-31) - press release, news stories, user reactions, review roundups, cast interviews

- Digital ads (Jan 16-Mar 16) - IG, FB, TikTok, YouTube, Display ads, in-app ads (3rd party apps)

# (III) PRODUCT MARKETING - Waitlist & User Growth

| # Channel | # Activities |
| --- | --- |
| # Paid Ads | # Meta + TikTok ads (Dec 1 - Jan 31). # Google/App Store ads post-launch. # Target: faith + African diaspora audiences. # Budget: $5,000 (3M impressions, 20K clicks, 600+ sign ups, Av. CPA $8) |
| # CRM/Email | # Waitlist nurture sequence (weekly email newsletters) # Launch announcement email (Jan 16). # Donor appeals (Dec 20, Jan 5). # Early user onboarding flow. |
| # Surprise & Delight | # Early access releases for the first 1000 waitlist (Dec 26 - Boxing day gift). # Exclusive content drops for early adopters. # Referral incentives programme |
| # Fundraising | # GiveSendGo campaign push. # Corporate donor outreach. # In-app donation prompts. # Event sponsorship/partnership packages. |

# (IV) CONTENT MARKETING & DIGITAL CHANNELS MANAGEMENT

## Festive Campaign: "The Gift" (Dec 1-31)

Continue #TheMissingPiece → #TheGiftToCome narrative.

Christmas-themed content celebrating FaithStream as “the gift for the family.”

Countdown to Jan 16 launch. Daily devotional teasers.

Key messages:

- Donors = “give someone a gift of the gospel in the form of entertainment by supporting FaithStream”

- Consumers = “here’s our gift to you this festive season, to give you joy and uplift your soul’

## Social Media (IG, FB, TikTok, X)

- Organic: 1-2 original posts/day across platforms. User testimonials, content teasers, behind-the-scenes, launch countdown

- Paid: Boost high-performing posts. Retargeting waitlist visitors. Launch week blitz

- Community: Engage comments/DMs within 2 hours. Share user-generated content. Host IG Lives with creators/cast/co-founders/influencers/volunteers

## Thought Leadership

Kunle & Hakeem bylined articles - blog and LinkedIn (1 each per week): faith-based media crisis, African entertainment opportunity. Podcast interviews (target 5+ between Dec & Jan e.g. Black Flame with Gaise Baba). Co-founder personal posts on launch milestones.

## Influencer Marketing

Christian creator partnerships (10-15 creators). Friendly reviews. Skit creation. Launch day coordinated posts. Premiere attendance. Ongoing ambassador relationships. Focus: faith-aligned, African diaspora, family content creators.

(V) KEY DATES & MILESTONES

- Dec 20: Guest/media invites sent

- Jan 2: Full trailer release

- Jan 10: Press kits distributed + media rounds

- Jan 16: LAGOS LAUNCH

- Jan 17-31: Post-launch media blitz + media rounds